Statement of Work

In support of

CyberGreen Global Cyber Health Measurement

1. Produce Bi-annual Metrics Analysis Report
2. Monthly index and support metrics analysis

Between:

CyberGreen Institute

93 Worth St, NYC, NY 10013, USA

+1.310.463.2776

Manel Medina

Address: Street Sta. Caterina, 2 – 08290-Cerdanyola V. – Barcelona (Spain)

Phone number: +34 605284388 / +34 934016984

THIS STATEMENT OF WORK ("Statement of Work"), dated as of the Effective Date indicated below, is issued pursuant to and incorporates the terms and conditions of the Services Agreement (the "Agreement") dated 1 June 2016, between the CyberGreen Institute ("Customer") and Manel Medina ("Consultant").

1. Project Description. The Consultant will perform the Services identified below for Customer.

The consultant will provide the Bi-annual CyberGreen Metrics Analysis Report (Publish in October and February), and monthly index and support metrics analysis.

2. Deliverables. The Consultant will be responsible for 2 tasks. The deliverables the Consultant will provide to Customer are identified below:

Task 1. Producing Bi-annual CyberGreen index analysis Reports (total 2 reports)

* Relating data collection and analysis of selected ASN/Country/Threats
  + Produce several views of Internet healthiness, from different perspectives, addressed to different target audiences: End users, Policy makers, and CSIRTs/Mitigators
  + First choice of threats: openNTP servers, openDNS servers, openSSDP servers (SPAM and Phishing sources/sites)
* 1st index analysis report delivery of October 2016
* 2nd index analysis report delivery of February, 2017
* Fetch feedback from relevant stakeholders about coherence, impact and usefulness of report content and format/visualization.

Task 2. Monthly global ecosystem health index short analysis memo (1-2 pages of significant findings or trends of the month)

* + Produce several views of Internet healthiness, from different perspectives. Target audiences: Capacity building “needs” analysis, Operations -
  + First choice of threats: openNTP servers, openDNS servers, openSSDP servers (SPAM and Phishing sources/sites)

**Tasks, Deliverables, Schedule and Costs:**

All proposed dates are understood as “Not Later Than,”

**Task One –** Data analysis of Bi-annual CyberGreen index analysis Reports

Deliverable: Bi-annual Reports

* Proposed Schedule:

(a) 1st Report draft for review on 30th September 2016

- Final 1st report by 25 October 2016

(b) 2nd Report draft for review on 15th February 2017

- Final 2nd report by 28th February 2017

* Task Cost – US$ 15,000

**Task Two –** Monthly global ecosystem health index short analysis memo

Deliverable: Monthly short analysis reports (July – Feb)

* Proposed Schedule:

- Monthly report delivered the end of business of last day of every month

(c) July, August, September, October memos delivered by 31st October

(d) November and December 2016, January and February 2017 monthly memos delivered by end of each month

**Intellectual Property:** CyberGreen and the Consultant agree on that all work produced as part of this effort is joint intellectual property, usable by either party at their own discretion, previous notification to the other party.

**Place of Performance**: The Consultant will perform work on this contract primarily at its own facilities.

**Cost:** Fixed fee purchase order, US$ 30,000

Payment shall be US$ 15,000 upon acceptance the delivery of (a) and (c).

And US$ 15,000 upon acceptance of the delivery of (b) and (d).

**Payment Disputes**.

An invoice will be deemed as accepted by CyberGreen unless CyberGreen notifies the Consultant of a dispute with such invoice in writing within fifteen (15) calendar days after receipt of the applicable invoice. Both Parties agree to use commercially reasonable efforts to resolve the disputed charges promptly.